## Spring
GANTT CHART | [24 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | [Team14] CryptoSentiment Pulse: Leveraging NLP for Social Media Analysis in Cryptocurrency Markets
[5 empty] | PHASE ONE | [34 empty] | PHASE TWO | [41 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2022-01-17 | [6 empty] | 2022-01-24 | [6 empty] | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04 | [6 empty] | 2022-04-11 | [6 empty] | 2022-04-18 | [6 empty] | 2022-04-25
[5 empty] | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
Project Team Composition | All | 2024-01-17 | 2024-02-02 | 15 | 2022-03-21 M: Spring Break
Project Proposal
Introduction & Background | Wei Hong, Ke Xin, Abhijith Sreeraj | 2024-02-02 | 2024-02-23 | 21 | bar: 2022-01-31 W to 2022-02-07 U
Problem Definition | Wei Hong, Joel J Jude | 2024-02-02 | 2024-02-23 | 21 | bar: 2022-01-31 W to 2022-02-07 U
Methods | Wei Hong, Ke Xin, Shinhaneg Lee | 2024-02-02 | 2024-02-23 | 21 | bar: 2022-01-31 W to 2022-02-07 U
Potential Dataset | Shinhaeng Lee, Abhijith Sreeraj | 2024-02-02 | 2024-02-23 | 21 | bar: 2022-01-31 W to 2022-02-07 U
Potential Results & Discussion | All | 2024-02-02 | 2024-02-23 | 21 | bar: 2022-01-31 W to 2022-02-07 U
Video Creation & Recording | Joel J Jude | 2024-02-10 | 2024-02-23 | 13 | bar: 2022-02-07 R to 2022-02-14 R
GitHub Page | Abhijith Sreeraj, Ke Xin | 2024-02-10 | 2024-02-23 | 13 | bar: 2022-02-07 R to 2022-02-14 R
Midterm Report
Data Cleaning, Preprocessing | Wei Hong | 2024-02-17 | 2024-02-27 | 10 | bar: 2022-02-07 R to 2022-02-07 U; 2022-02-14 F to 2022-02-21 U
Data Visualization | Abhijith Sreeraj, Joel J Jude | 2024-02-17 | 2024-02-27 | 10 | bar: 2022-02-07 R to 2022-02-07 U; 2022-02-14 F to 2022-02-21 U
Model 1 (M1) Design & Selection [ElKulako_stocktwits_crypto_finetune] | Wei Hong, Ke Xin | 2024-02-17 | 2024-02-27 | 10 | bar: 2022-02-07 R to 2022-02-07 U; 2022-02-14 F to 2022-02-21 U
M1 Implementation & Coding | Wei Hong | 2024-02-28 | 2024-03-17 | 19 | bar: 2022-02-07 R to 2022-02-07 U; 2022-02-28 M to 2022-03-14 U
M1 Results Evaluation | All | 2024-03-14 | 2024-03-20 | 6 | bar: 2022-02-07 R to 2022-02-07 U; 2022-03-14 M to 2022-03-14 U
Model 2 (M2) Design & Selection [kk08_cryptobert_finetune] | Ke Xin | 2024-02-28 | 2024-03-06 | 8 | bar: 2022-02-07 R to 2022-02-07 U; 2022-02-28 M to 2022-02-28 W
M2 Implementation & Coding | Ke Xin | 2024-02-28 | 2024-03-17 | 19 | bar: 2022-02-07 R to 2022-02-07 U; 2022-02-28 M to 2022-03-14 U
M3 implementation & Coding [BiLSTM] | Shinhaeng Lee | 2024-02-28 | 2024-03-06 | 8 | bar: 2022-02-07 R to 2022-02-07 U; 2022-02-28 M to 2022-02-28 U
M3 Coding & Implementation | Shinhaeng Lee | 2024-02-28 | 2024-03-06 | 8 | bar: 2022-02-07 R to 2022-02-07 U; 2022-02-28 M to 2022-02-28 U
M4 implementation & Coding [Kmeans, Birch, HDBscan] | Abhijith Sreeraj, Joel J Jude | 2024-03-07 | 2024-03-17 | 10 | bar: 2022-02-07 R to 2022-02-07 U; 2022-03-07 M to 2022-03-14 U
M1, M2 Results Evaluation | All | 2024-03-18 | 2024-03-20 | 2 | bar: 2022-02-07 R to 2022-02-07 U; 2022-03-14 F to 2022-03-14 U
Midterm Report | All | 2024-03-25 | 2024-03-29 | 4 | bar: 2022-02-07 R to 2022-02-07 U; 2022-03-14 S to 2022-03-14 U; 2022-03-28 M to 2022-03-28 T
Final Report
M3 refinement & analysis [BiLSTM] | Shinhaeng Lee | 2024-03-14 | 2024-03-20 | 6 | bar: 2022-02-07 R to 2022-02-07 U; 2022-03-14 M to 2022-03-14 U; 2022-03-28 M to 2022-03-28 U
M4 refinement & analysis [Kmeans, Birch, HDBscan] | Abhijith Sreeraj | 2024-03-14 | 2024-03-20 | 6 | bar: 2022-02-07 R to 2022-02-07 U; 2022-03-14 M to 2022-03-14 U; 2022-03-28 M to 2022-03-28 U
M4 Results Evaluation | Abhijith Sreeraj | 2024-03-14 | 2024-03-20 | 6 | bar: 2022-02-07 R to 2022-02-07 U; 2022-04-04 M to 2022-04-11 W
M3 Results Evaluation | Shinhaeng Lee | 2024-03-14 | 2024-03-20 | 6 | bar: 2022-02-07 R to 2022-02-07 U; 2022-04-04 M to 2022-04-11 W
M1-M4 Comparison | All | 2024-04-18 | 2024-04-19 | 1 | bar: 2022-02-07 R to 2022-02-07 U; 2022-04-11 R to 2022-04-25 T
Final presentation | Abhijith Sreeraj, Shinhaeng Lee, Wei Hong Low, Ke Xin Chong | 2024-04-18 | 2024-04-26 | 8 | bar: 2022-02-07 R to 2022-02-07 U; 2022-04-18 R to 2022-04-25 T
Final Report | All | 2024-04-18 | 2024-04-23 | 5 | bar: 2022-02-07 R to 2022-02-07 U; 2022-04-18 R to 2022-04-25 T

## Fall
GANTT CHART | [24 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | NHL Playoff Predictor
[5 empty] | PHASE ONE | [13 empty] | PHASE TWO | [34 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2021-09-27 | [6 empty] | 2021-10-04 | [6 empty] | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22 | [6 empty] | 2021-11-29 | [6 empty] | 2021-12-06
[5 empty] | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
Project Proposal
Introduction & Background | Karishma | 2021-09-27 | 2021-10-04 | 7 | bar: 2021-09-27 M to 2021-09-27 U
Problem Definition | Tim | 2021-09-27 | 2021-10-04 | 7 | bar: 2021-09-27 M to 2021-09-27 U
Methods | Bryan | 2021-09-27 | 2021-10-04 | 7 | bar: 2021-09-27 M to 2021-09-27 U
Potential Results & Discussion | Noah & Gabby | 2021-09-27 | 2021-10-04 | 7 | bar: 2021-09-27 M to 2021-09-27 U
Video Recording | All | 2021-10-04 | 2021-10-07 | 3 | bar: 2021-10-04 M to 2021-10-04 W
GitHub Page | Karishma | 2021-10-04 | 2021-10-07 | 3 | bar: 2021-10-04 M to 2021-10-04 W
Model 1
Data Sourcing and Cleaning | Tim | 2021-10-07 | 2021-10-15 | 8 | bar: 2021-10-04 R to 2021-10-11 R
Model Selection | Karishma | 2021-10-15 | 2021-10-18 | 3 | bar: 2021-10-11 F to 2021-10-11 U
Data Pre-Processing | Tim | 2021-10-18 | 2021-10-25 | 7
Model Coding | Karishma | 2021-10-25 | 2021-11-08 | 13 | bar: 2021-10-25 M to 2021-11-01 U
Results Evaluation and Analysis | Tim | 2021-11-08 | 2021-11-16 | 8 | bar: 2021-11-08 M to 2021-11-15 M
Midterm Report | All | 2021-11-08 | 2021-11-16 | 8 | bar: 2021-11-08 M to 2021-11-15 M
Model 2
Data Sourcing and Cleaning | Gabby | 2021-10-18 | 2021-10-22 | 4 | bar: 2021-10-18 M to 2021-10-18 R
Model Selection | Noah | 2021-10-22 | 2021-10-25 | 3 | bar: 2021-10-18 F to 2021-10-18 U
Data Pre-Processing | Gabby | 2021-10-25 | 2021-10-29 | 4 | bar: 2021-10-25 M to 2021-10-25 R
Model Coding | Noah | 2021-10-25 | 2021-11-19 | 24 | bar: 2021-10-25 F to 2021-11-01 U; 2021-11-15 T to 2021-11-15 R
Results Evaluation and Analysis | Gabby | 2021-11-19 | 2021-11-24 | 5 | bar: 2021-11-15 F to 2021-11-22 T
Model 3
Data Sourcing and Cleaning | Bryan | 2021-10-18 | 2021-10-22 | 4 | bar: 2021-10-18 M to 2021-10-18 R
Model Selection | Bryan | 2021-10-22 | 2021-10-25 | 3 | bar: 2021-10-18 F to 2021-10-18 U
Data Pre-Processing | Bryan | 2021-10-25 | 2021-10-29 | 4 | bar: 2021-10-25 M to 2021-10-25 R
Model Coding | Bryan | 2021-10-25 | 2021-11-19 | 24 | bar: 2021-10-25 F to 2021-11-01 U; 2021-11-15 T to 2021-11-15 R
Results Evaluation and Analysis | Bryan | 2021-11-19 | 2021-11-24 | 5 | bar: 2021-11-15 F to 2021-11-22 T
Evaluation
Model Comparison | Tim | 2021-11-29 | 2021-12-07 | 8 | bar: 2021-11-29 M to 2021-12-06 M
Presentation | All | 2021-11-29 | 2021-12-06 | 7 | bar: 2021-11-29 M to 2021-11-29 U
Recording | All | 2021-12-06 | 2021-12-07 | 1 | bar: 2021-12-06 M
Final Report | All | 2021-11-29 | 2021-12-07 | 8 | bar: 2021-11-29 M to 2021-12-06 M

## Fall Overview
GANTT CHART | [7 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | NHL Playoff Predictor
[5 empty] | PHASE ONE |  | PHASE TWO | [5 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2021-09-27 | 2021-10-04 | 2021-10-11 |  | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06
Project Proposal |  | 2021-09-27 | 2021-10-07 | 10
Introduction & Background | Karishma | 2021-09-27 | 2021-10-04 | 7
Problem Definition | Tim | 2021-09-27 | 2021-10-04 | 7
Methods | Bryan | 2021-09-27 | 2021-10-04 | 7
Potential Results & Discussion | Noah & Gabby | 2021-09-27 | 2021-10-04 | 7
Video Recording | All | 2021-10-04 | 2021-10-07 | 3
GitHub Page | Karishma | 2021-10-04 | 2021-10-07 | 3
Model 1 |  | 2021-10-07 | 2021-11-16 | 39
Data Sourcing and Cleaning | Tim | 2021-10-07 | 2021-10-15 | 8
Model Selection | Karishma | 2021-10-15 | 2021-10-18 | 3
Data Pre-Processing | Tim | 2021-10-18 | 2021-10-25 | 7
Model Coding | Karishma | 2021-10-25 | 2021-11-08 | 13
Results Evaluation and Analysis | Tim | 2021-11-08 | 2021-11-16 | 8
Midterm Report | All | 2021-11-08 | 2021-11-16 | 8
Model 2 |  | 2021-10-18 | 2021-11-24 | 36
Data Sourcing and Cleaning | Gabby | 2021-10-18 | 2021-10-22 | 4
Model Selection | Noah | 2021-10-22 | 2021-10-25 | 3
Data Pre-Processing | Gabby | 2021-10-25 | 2021-10-29 | 4
Model Coding | Noah | 2021-10-25 | 2021-11-19 | 24
Results Evaluation and Analysis | Gabby | 2021-11-19 | 2021-11-24 | 5
Model 3 |  | 2021-10-18 | 2021-11-24 | 36
Data Sourcing and Cleaning | Bryan | 2021-10-18 | 2021-10-22 | 4
Model Selection | Bryan | 2021-10-22 | 2021-10-25 | 3
Data Pre-Processing | Bryan | 2021-10-25 | 2021-10-29 | 4
Model Coding | Bryan | 2021-10-25 | 2021-11-19 | 24
Results Evaluation and Analysis | Bryan | 2021-11-19 | 2021-11-24 | 5
Evaluation |  | 2021-11-24 | 2021-12-07 | 13
Model Comparison | Tim | 2021-11-29 | 2021-12-07 | 8
Presentation | All | 2021-11-29 | 2021-12-06 | 7
Recording | All | 2021-12-06 | 2021-12-07 | 1
Final Report | All | 2021-11-29 | 2021-12-07 | 8